## Fall
GANTT CHART | [24 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Geo-Guesser AI
[5 empty] | PHASE ONE | [13 empty] | PHASE TWO | [34 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2022-09-30 | [6 empty] | 2022-10-07 | [6 empty] | 2022-10-14 | [6 empty] | 2022-10-21 | [6 empty] | 2022-10-28 | [6 empty] | 2022-11-04 | [6 empty] | 2022-11-11 | [6 empty] | 2022-11-18 | [6 empty] | 2022-11-25 | [6 empty] | 2022-12-02 | [6 empty] | 2022-12-09
[5 empty] | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U | M | T | W | R | F | S | U
Project Proposal
Introduction & Background | David | 2022-10-04 | 2022-10-07 | 3 | bar: 2022-09-30 M to 2022-09-30 U
Problem Definition | David | 2022-10-04 | 2022-10-07 | 3 | bar: 2022-09-30 M to 2022-09-30 U
Methods | Ani and Sameer | 2022-10-04 | 2022-10-07 | 3 | bar: 2022-09-30 M to 2022-09-30 U
Potential Results & Discussion | Adithya and Wesley | 2022-10-04 | 2022-10-07 | 3 | bar: 2022-09-30 M to 2022-09-30 U
Video Recording | All | 2022-10-04 | 2022-10-07 | 3
GitHub Page | David | 2021-10-04 | 2021-10-07 | 3
Model 1
Data Sourcing and Cleaning | Anirudh and David | 2022-10-09 | 2022-10-16 | 7 | bar: 2022-10-07 R to 2022-10-14 R
Model Selection | Sameer | 2022-10-15 | 2022-10-18 | 3 | bar: 2022-10-14 F to 2022-10-14 U
Data Pre-Processing | Adithya | 2022-10-18 | 2022-10-25 | 7
Model Coding | All | 2022-10-25 | 2022-11-08 | 13 | bar: 2022-10-28 M to 2022-11-04 U
Results Evaluation and Analysis | Wesley | 2022-11-08 | 2022-11-16 | 8 | bar: 2022-11-11 M to 2022-11-18 M
Midterm Report | All | 2022-11-08 | 2022-11-16 | 8 | bar: 2022-11-11 M to 2022-11-18 M
Model 2
Data Sourcing and Cleaning | Sameer and Adithya | 2022-10-09 | 2022-10-16 | 7 | bar: 2022-10-21 M to 2022-10-21 R
Model Selection | Wesley | 2022-10-15 | 2022-10-25 | 10 | bar: 2022-10-21 F to 2022-10-21 U
Data Pre-Processing | Anirudh | 2022-10-18 | 2022-11-08 | 20 | bar: 2022-10-28 M to 2022-10-28 R
Model Coding | All | 2022-11-08 | 2022-11-16 | 8 | bar: 2022-10-28 F to 2022-11-04 U; 2022-11-18 T to 2022-11-18 R
Results Evaluation and Analysis | David | 2022-11-08 | 2022-11-16 | 8 | bar: 2022-11-18 F to 2022-11-25 T
Model 3
Data Sourcing and Cleaning | Wesley | 2022-10-18 | 2022-10-22 | 4 | bar: 2022-10-21 M to 2022-10-21 R
Model Selection | David and Adithya | 2022-10-22 | 2022-10-25 | 3 | bar: 2022-10-21 F to 2022-10-21 U
Data Pre-Processing | Sameer | 2022-10-25 | 2022-10-29 | 4 | bar: 2022-10-28 M to 2022-10-28 R
Model Coding | All | 2022-10-25 | 2022-11-19 | 24 | bar: 2022-10-28 F to 2022-11-04 U; 2022-11-18 T to 2022-11-18 R
Results Evaluation and Analysis | All | 2022-11-19 | 2022-11-24 | 5 | bar: 2022-11-18 F to 2022-11-25 T
Evaluation
Model Comparison | All | 2022-11-29 | 2022-12-07 | 8 | bar: 2022-12-02 M to 2022-12-09 M
Presentation | All | 2022-11-29 | 2022-12-06 | 7 | bar: 2022-12-02 M to 2022-12-02 U
Recording | All | 2022-12-06 | 2022-12-07 | 1 | bar: 2022-12-09 M
Final Report | All | 2022-11-29 | 2022-12-07 | 8 | bar: 2022-12-02 M to 2022-12-09 M

## Contribution Table
TASK TITLE | TASK OWNER | TASK TITLE | TASK OWNER | Task Title | Task Owner
Project Proposal | All | Midterm Report | All | Final Report | All
Introduction & Background | David | Data Sourcing and Cleaning | Anirudh and David | Model 2 creation using extra layers in the CNN | David and Ani
Problem Definition | David | Data Pre-Processing | Adithya
Methods | Sameer and Ani | Model Coding | All
Potential Results & Discussion | Adithya and Wesley | Model Selection | Sameer | Updated Feature selection | Wesley and Sameer
Video Recording | All | Results Evaluation/Analysis | Wesley
GitHub Page | All | Midterm Report | All | Hyperparameter tuning | Adithya
|  |  |  | Midterm Report | All
|  |  |  | Video | All

## Fall Overview
GANTT CHART | [7 empty] | https://goo.gl/PXLbMe
PROJECT TITLE | Country Predictor Based on StreetView Images
[5 empty] | PHASE ONE |  | PHASE TWO | [5 empty] | PHASE THREE
TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | 2021-09-27 | 2021-10-04 | 2021-10-11 |  | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06
Project Proposal |  | 2021-09-27 | 2021-10-07 | 10
Introduction & Background | Karishma | 2021-09-27 | 2021-10-04 | 7
Problem Definition | Tim | 2021-09-27 | 2021-10-04 | 7
Methods | Bryan | 2021-09-27 | 2021-10-04 | 7
Potential Results & Discussion | Noah & Gabby | 2021-09-27 | 2021-10-04 | 7
Video Recording | All | 2021-10-04 | 2021-10-07 | 3
GitHub Page | Karishma | 2021-10-04 | 2021-10-07 | 3
Model 1 |  | 2021-10-07 | 2021-11-16 | 39
Data Sourcing and Cleaning | Tim | 2021-10-07 | 2021-10-15 | 8
Model Selection | Karishma | 2021-10-15 | 2021-10-18 | 3
Data Pre-Processing | Tim | 2021-10-18 | 2021-10-25 | 7
Model Coding | Karishma | 2021-10-25 | 2021-11-08 | 13
Results Evaluation and Analysis | Tim | 2021-11-08 | 2021-11-16 | 8
Midterm Report | All | 2021-11-08 | 2021-11-16 | 8
Model 2 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Gabby | 2021-10-18 | 2021-10-22 | 4
Model Selection | Noah | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Gabby | 2021-10-25 | 2021-10-29 | 4
Model Coding | Noah | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Gabby | 2021-11-19 | 2021-11-24 | 5
Model 3 |  | 2021-10-18 | 2021-11-24 | 36
Data Sourcing and Cleaning | Bryan | 2021-10-18 | 2021-10-22 | 4
Model Selection | Bryan | 2021-10-22 | 2021-10-25 | 3
Data Pre-Processing | Bryan | 2021-10-25 | 2021-10-29 | 4
Model Coding | Bryan | 2021-10-25 | 2021-11-19 | 24
Results Evaluation and Analysis | Bryan | 2021-11-19 | 2021-11-24 | 5
Evaluation |  | 2021-11-24 | 2021-12-07 | 13
Model Comparison | Tim | 2021-11-29 | 2021-12-07 | 8
Presentation | All | 2021-11-29 | 2021-12-06 | 7
Recording | All | 2021-12-06 | 2021-12-07 | 1
Final Report | All | 2021-11-29 | 2021-12-07 | 8